## BLANK - Sprint Planning
SPRINT PLANNING
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE | Power BI dashboards, KPI reports, Sprint sheets, Test Cases
Revenue & Payment Analysis Dashboard |  |  | Dilip Choudhary |  | 2025-08-01 | 2025-09-04 | 60% | SCOPE STATEMENT | Build a comprehensive dashboard to track customer revenue, outstanding payments, and payment behaviors; implement KPIs, metrics, and predictive insights for financial decision-making.
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
SPRINT 1
No | Collect & Clean Customer Data | Data prep | You | 3 | 2025-08-01 | 2025-08-03 | 3 | Complete | High
No | Collect & Clean Transactions Data | Data prep | You | 3 | 2025-08-01 | 2025-08-04 | 4 | Complete | High
SPRINT 2
No | Define KPIs & Metrics | KPI Analysis | You | 2 | 2025-08-08 | 2025-08-09 | 2 | Complete | High
No | Create Data Model in Power BI | Dashboard | You | 3 | 2025-08-10 | 2025-08-12 | 3 | Complete | High
SPRINT 3
No | Build Power BI Dashboard | Dashboard | You | 2 | 2025-08-15 | 2025-08-19 | 5 | Complete | High
No | Dashboard Testing | Testing | You | 5 | 2025-08-20 | 2025-08-21 | 2 | Complete | High
SPRINT 4
No | Revenue & Payment Insights Analysis | Analysis | You | 3 | 2025-08-22 | 2025-08-25 | 4 | Complete | Medium
No | Recommendations & Report Preparation | Reporting | You | 2 | 2025-08-26 | 2025-08-28 | 3 | Complete | Medium
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Dropdown Keys - Do Not Delete - (hidden)
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold