## User Acceptance Testing (UAT) D
User Acceptance Testing (UAT) Document
Document Version: 1.0
Date: September 03, 2025
Prepared By: Dilip
Project Reference: BRD-XYZ-001 (Dated August 25, 2025)
Last Updated: September 03, 2025
1. Introduction | 2. Project Overview 2.1 Business Problem Delayed payments and revenue risks are impacting ABC Company’s cash flow. The dashboard aims to replace manual Excel tracking with real-time AR monitoring and analytics-driven improvements. 2.2 Solution Summary A Power BI-based AR monitoring dashboard with: Real-time tracking of invoices and overdue balances. Risk identification for overdue >30 days. DSO trend analysis and payment behavior insights. Automated alerts and weekly reports for stakeholders.
1.1 Purpose
This UAT document outlines the process to validate that the Revenue Insights Dashboard meets the business requirements defined in the BRD (R001–R005) and is ready for production use by ABC Company stakeholders. The goal is to ensure the dashboard accurately tracks revenue, identifies risks, and supports decision-making for collections.
1.2 Scope
In Scope:
Validation of KPIs (e.g., Total Revenue, Outstanding Revenue), interactivity (filters by country/tier), data accuracy, usability, and performance.
Out of Scope:
Live ERP integration, mobile testing, and advanced features (e.g., fraud KPIs from Sprint 5).
|  | Role | Participant(s) | Responsibilities
1.3 Objectives: |  | UAT Lead | Dilip | Coordinate testing, track defects, sign-off.
Validate all functional requirements (R001–R005). |  | Testers | Finance Team, CFO | Execute test cases, validate business needs.
Confirm KPI accuracy against source data. |  | Support Team | IT/BI Team (XYZ) | Resolve defects, provide dashboard access.
Ensure the dashboard is user-friendly and supports business decisions. |  | Approver | CFO | Review results and provide final sign-off.
Achieve 100% pass rate on critical test cases.

## UAT Results
UAT Test Case
Test Case ID | Scenario ID | Description | Precondition | Steps | Expected Result | Actual Result | Status
TC_001 | UAT_001 | Verify total revenue matches transaction data | Clean dataset loaded into Power BI | 1. Open dashboard → Revenue summary2. Cross-check with Excel totals | Dashboard total revenue matches Excel total (₹38,64,000) | As Expected | Pass
TC_002 | UAT_002 | Verify overdue >30 days correctly flagged as high-risk | Same dataset | 1. Apply "overdue >30 days" filter2. Review flagged clients | All flagged clients have overdue days >30 | As Expected | Pass
TC_003 | UAT_003 | Verify DSO formula accuracy | Same dataset | 1. Review monthly DSO chart2. Validate sample calculations manually | Dashboard DSO matches manual calculations within 0.5% | As Expected | Pass
TC_004 | UAT_004 | Verify revenue at risk matches total outstanding | Dataset ready | 1. View "Outstanding Revenue" visual2. Cross-check totals | Dashboard matches source dataset values exactly | As Expected | Pass
TC_005 | UAT_005 | Verify recommendations display correctly | Dataset loaded | 1. Review recommendations section2. Validate top customers & overdue amounts | Recommendations match top overdue client data | As Expected | Pass
Defect ID | Description | Severity | Status | Assigned To | Resolution
DEF-001 | [e.g., Filter not working] | [High] | Closed | [IT/BI Team] | Resolved
Acceptance Criteria
100% pass rate on all test cases (TC_001–TC_005).
No critical or high-severity defects unresolved.
Stakeholder approval on usability and business fit.