## UAT Sceneario
UAT Test Scenarios
Test Environment |  | Scenario ID | Scenario Name | Requirement Mapping
Tool: Power BI Desktop/Service (.pbix file). |  | UAT_001 | Validate total revenue calculation | R001
Data: Sample dataset (6–12 months of invoices/payments). |  | UAT_002 | Identify high-risk customers correctly (overdue >30 days) | R002
Access: View-only for testers; shared via secure link. |  | UAT_003 | Verify DSO calculation for each month | R003
Preconditions: Dashboard loaded with data; training completed. |  | UAT_004 | Confirm revenue at risk matches outstanding | R004
|  | UAT_005 | Verify collection recommendations and strategy suggestions | R005
Test Schedule
Phase | Date | Activities
Preparation | Aug 26–30, 2025 | Setup, training (Oct 1, 07:30 AM IST).
Execution | Sep 1–7, 2025 | Run test cases, log defects.
Defect Resolution | Sep 8, 2025 | Fix and retest defects.
Sign-Off | Sep 9, 2025 | Final review and approval.